## Blad1
WEEK | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 5 | WEEK 6 | WEEK 7 | WEEK 8 | WEEK 9 | WEEK 10
|  | PRESENTATIE |  | VACATION
Movement Class | WEEK 1: Movement Class; WEEK 2: Wave Class; WEEK 3: Spawning Class | Rief
Shooting Class | WEEK 1: Basic AI; WEEK 2: Navmesh/A*; WEEK 3: Sounds; WEEK 5: Sounds; WEEK 6: Skybox | Tom
Basic AI | WEEK 1: UI Elements; WEEK 2: Shooting Class; WEEK 3: Particles; WEEK 5: Particles | Arne
Navmesh/A* | Level Design | Level Design | Level Design |  | Level Design | Level Design | Level Design | Level Design | Level Design | Level Design | Thomas
UI Elements | Objects | Objects | Objects |  | Objects | Objects | Objects | Objects | Objects | Objects | Lucas
Particles | WEEK 2: Enemy Animating; WEEK 3: Enemy Texturing; WEEK 5: Pistol Animating
Wave Class | Objects | Objects | Objects |  | Objects | Objects | Objects | Objects | Objects | Objects
Spawning Class | WEEK 1: Enemy Modeling; WEEK 2: Pistol Modeling
Skybox | WEEK 1: Enemy Rigging; WEEK 2: Pistol Texturing
Enemy Modeling
Enemy Texturing
Enemy Rigging
Enemy Animating
Objects
Pistol Modeling
Pistol Texturing
Pistol Animating
Level Design